## project
Project Planner
					Period Highlight:					1				Plan			Actual				% Complete					Actual (beyond plan)					% Complete (beyond plan)

	PLAN	PLAN	ACTUAL	ACTUAL	PERCENT	Start date	end date
ACTIVITY	START	DURATION	START	DURATION	COMPLETE				PERIODS
					1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35	36	37	38	39	40	41	42	43	44	45	46	47	48	49	50	51	52	53	54	55	56	57	58	59	60	61	62	63	64	65	66	67	68	69	70	71	72	73	74	75	76	77	78	79	80	81	82	83	84	85	86	87	88	89	90	91	92	93	94	95	96	97	98	99	100	101	102	103	104	105	106	107	108	109	110	111	112	113	114	115	116	117	118	119	120	121	123	124	125	126	127	128	129	130	131	132	134	135	136	137	138	139	140	141	142	143	144	145	146	147	148	149	150	151	152	153	154	155	156	157	158	159	160	161	162	163	164	165	166	167	168	169	170	171	172	173	174	175	176	177	178	179	180	181	182	183	184	185	186	187	188	189	190	191	192	193	194	195	196	197	198	199	200	201	202	203	204	205	206	207	208	209	210	211	212	213	214	215	216	217	218	219	220	221	222	223	224	225	226	227	228	229	230	231	232	233	234	235	236	237	238	239	240	241	242	243	244	245	246	247	248	249	250	251	252	253	254	255	256	257	258	259	260	261	262	263	264	265	266	267	268	269	270	271	272	273	274	275	276	277	278	279	280	281	282	283	284	285	286	287	288	289	290	291	292	293	294	295	296	297	298	299	300	301	302	303	304	305	310	311	312	313	314	315	316	317	318	319	320	321	322	323	324	325	326	327	328	329	330	331	332	334	335	336	337	338	339	340	341	342	343	344	345	346	347	348	349	350	351	352	353	354	355	356	357	358	359	360	361	362	363	364	365	366	367	368	369	370	371	372	373	375	376	377	378	379	380	381	382	383	384	385	386	387	388	389	390	391	392	393	394	395	396	397	398	399	400	401	402	403	404	405	406	407	408	409	410	411	412	413	414	415	417	418	419	420	421	422	423	424	425	426
creating a project plan	1	20			0%	10.10.2016	4.11.2016
creating a presentation	21	5				25.10.2016	4.11.2016
prepare for presentation	26	5				3.11.2016	4.11.2016
Similar in the field
research	31	8				10.10.2016	11.11.2016
document findings	39	5				11.11.2016	13.11.2016
Background resources
relavant books	44	5				11.11.2016	13.11.2016
articles and online resources	49	5				11.11.2016	13.11.2016
define hardware requirements	54	5				14.11.2016	18.11.2016
document hardware requirements	59	2				18.11.2016	19.11.2016
research virtual machine deployment with virtualbox and shell scripting	61	13				19.11.2016	25.11.2016
proof of concept shell deployment script	74	8				26.11.2016	05.12.2016
research virtual machine caching	82	3				06.12.2016	07.12.2016
read Uncomplicated Firewall man pages	85	3				08.12.2016	10.12.2016
research network/disk/cpu/temperature monitors	88	3				11.12.2016	11.12.2016
research web frameworks for rapid development, strong api support that prefer convention over configuration	91	3				11.11.2016	12.12.2016
generate ssh keys on the guest operating system	94	3
connect to a remote machine and copy the ssh keys	97	3
remote machine connects to the remote machine with the ssh keys	97	3
create list of required APIs	100	3
create poster	103	13
write shell script for installing popular linux distros on the virtual machine host	116	13
write test script that verifies the instances are alive	129	13
document findings in dissertation	142	5
write shell script for installing software (apache, mysql, text editors	147	10
test and verify the integrity of the installed software	157	8
document findings	165	5
create firewall management shell script	170	5
test firewall configuration	175	10
document findings	185	5
create script for adding new keys with a name and password	190	3
script to obtain key by name	193	3
delete key	196	3
test key functionality	199	13
document behaviour	212	5
install perf monitoring software	217	8
create manual tests to verify correct reading	225	10
document behaviour	235	5
create website design	240	10
document design descisions	250	5
pick web technologies (database, API and components)	255	5
implement base web features	260	10
wrate base website tests	270	10
document behaviour	280	5
web api for interacting with the shell scripts	285	13
test web api	298	18
document findings	315	5
implement create vm interface	319	13
implement list vm interface	331	5
implement delete virtual machine instance interface	335	5
test create list and delete behaviour	339	20
manage ssh keys web interface implementation	358	5
install additional software interface	362	10
monitor performance with graphs interface	371	20
test ssh keys, software installation and performance monitoring	390	20
document behavioru	409	20