## Slide 1: Stage 3 Project: Aims and Objectives, and Planning
Some material adapted from Berndtsson et al, Dawson

## Slide 2: Remember …
Your Stage 3 Project is
  Not just a large piece of coursework
  Demanding, challenging, rewarding
  Culmination of 3 years’ study at Newcastle
  Chance to show what you can do
    extending beyond material you’ve been taught
  What you will tell employers about at interview

## Slide 3: Doing a Project
Most Ness project specifications are NOT specifications
  usually just a rough idea!
You need to define (with the supervisor) the project’s aim (or hypothesis), objectives, major tasks and milestones, and plan how to achieve them
First: understand the original project definition (what the supervisor/proposer was thinking may be different to what has been written down)
Notes: Part of objectives will be what the supervisor is expecting.
Plan for presentations as well as other things.
You must use the plan.
Software development models: code&fix (no), vs. waterfall, vs evolutionary. Use of prototypes. Depends on type of project. Program formatter: do careful spec. beforehand - waterfall. Visual editor: prototyping or evolutionary.
Apply the things you learned in the group project - did you learn anything about planning?
Milestones - so you can measure your own progress
Deliverables, so your supervisor can check on your (lack of) progress.
Fallback positions for when (if?) things go wrong
Stage 3: Project is expected to occupy 300 hours minimum
  12 hours per week on average! (Say 25 weeks)

## Slide 4: Project Aim
Should be a single, high-level statement of the hypothesis the project is investigating, or what the overall goal of the project is:
  e.g. “reduce the security risks that threaten internet voting”
Objectives are then smaller sub-goals for the project: achieve them, and you achieve your aim

## Slide 5: Project Objectives
The objectives contribute to the hypothesis or aim:
  Each objective should be a small sub-goal for the project: achieve them all, and you will achieve your aim
  Objectives will be returned to in your evaluation of your work
  Having 4 to 6 objectives is usually enough – fewer suggests inadequate depth, and more tends to turn into a list of requirements.
May be personal objectives as well as technical ones
Example objectives
  To review the issue of Web Accessibility from the perspective of the Web developer
  To build a prototype of a new design tool

## Slide 6: SMART Objectives
Objectives should be SMART:
  Specific
  Measurable,
  Achievable,
  Relevant
  Time-bound
Measurable so that you can say whether each objective has been achieved
Think about how to achieve as well as how to validate
Objectives should not be requirements, nor low-level tasks
https://en.wikipedia.org/wiki/SMART_criteria

## Slide 7: Some examples ...

## Slide 8: Good or bad?
Title: Student Voices: Documenting the First Year Student Experience On-line
Aims and Objectives
  Good Web Design
  Possible Technologies
  Data collection
No aim.
Not objectives – just some initial ideas about tasks
Better..?
Aim: to provide a means of recording first-year student experience
Objectives:
Review common problems experienced by first year students
Establish possible technology options for recording experience...
Notes: No aim.
Not objectives – just some initial ideas
about tasks
Better?
Aim: to provide a means of recording
first-year student experience
Objectives:
. Review common problems
experienced by first year students
. Establish possible technology
options for recording experience

## Slide 9: Good or bad?
Aim is to develop a tool to support students learning techniques for problem solving.
Objectives:
  Select a range of problems that can be used to illustrate problem solving.
  Allow a user’s progress with the tool to be recorded.
  Provide useful user feedback.
  Incorporate ideas from computer Aided learning.
  Provide a wide range of problems at different levels.
  Ensure the tool is easy to use.
  Tool should be extendable i.e. easy to add new problem scenarios.
Starts well, but then becomes tool requirements

## Slide 10: Objectives should not be requirements ...
Aim: Investigate the use of software to keep users motivated to carry out physical activity throughout their life.
Objectives:
  Allow users of the gym to record their activities in a simple way.
  Allow the user to get meaningful analysis of his physical activities that permits him to review past performance as well as analyses what he should be training next.
  Allow remote logging of exercises by building a web based version.
  Allow the user to synchronise the exercises entered online with the version at home.
  Build an Android phone application.
Requirements are to do with the details of what you are building.
You can only state requirements after the background research, and when you are working on the detail of what you are going to do.
Weasel word

## Slide 11: Aim should be a high-level summary, single research question
Aims:
To model and simulate a large scale election using the FOO Scheme.
To analyse the performance and scalability of the e-voting scheme.
To analyse the vulnerabilities of the scheme including the affects of:
  Multiple Voting
  Denial of Service Attacks
  Replay attacks
Objectives
Research current schemes available including published analysis of those schemes.
Implement the FOO e-voting scheme using the Java programming language including a system to simulate an election.
Simulate and analyse a large scale election
Aim: An analysis of the performance, vulnerabilities and scalability of the Fujioka Okamoto Ohta (FOO) e-voting scheme
Objectives:
Research and summarise published analysis of current e-voting schemes
Establish candidate set of vulnerabilities to investigate
Implement the FOO e-voting scheme
Use the implementation to simulate a large scale election
Analyse the performance and vulnerabilities of the FOO implementation
Notes: Aim: An analysis of the performance, vulnerabilities and scalability of the Fujioka Okamoto Ohta (FOO) e-voting scheme
Objs:
Research and summarise published analysis of current e-voting schemes
Establish candidate set of vulnerabilities to investigate
Implement the FOO e-voting scheme
Use the implementation to simulate a large scale election
Analyse the performance and vulnerabilities of the FOO implementation

## Slide 12: One more example...
Aims
  To investigate how the use of spatial regions on amalgamated tabletops can improve productivity and user interaction during meetings through the use of prototypes and participant observation
Objectives
  Investigate current applications/case studies of the use of interactive tabletops.
  Understand the needs of different types of meetings, such as roles, activities, responsibilities and how they need to be catered for.
  Conduct a user study through participant observation.
  Collect further qualitative information from users through the use of questionnaires and interviews to elaborate on desires/worries/issues with technology.
  Produce a paper prototype based on user study results and simulate operation with the usergroup, using the “Wizard of Oz” approach to enhance the user experience

## Slide 13: How to plan
You already have some deadlines to include in your plan:
  Final dissertation, Poster, Proposal (technical writing), Presentation, …
From these hard deadlines you can define tasks:
  Prepare draft reports, prepare poster, …
and minor deadlines:
  Submit draft to supervisor, …
You also need to define specific tasks to achieve your objectives, so identify:
  what work is to be done (by which method?)
  in what order, and
  how long it will all take
Notes: The role of a software development process model here..?

## Slide 14: Some tasks:
For the objective
  “To review the issue of Web Accessibility from the perspective of the Web developer”
Tasks might include
  identify the disabilities that can impair standard Web browsing
  evaluate the various Web accessibility tools
  build an accessible prototype

## Slide 15: Work Breakdown
Work Breakdown Structure (WBS):
Investigate Web Accessibility
…
Evaluate Accessibility Tools
Build Accessible Prototype Website
…
Set criteria for tool evaluation
Draw up list of tools
Evaluate and compare tools
Identify Disabilities
…
…
…
Establish requirements
for prototype(s)
…

## Slide 16: Time estimates and Milestones
List the lowest-level activities in the Work Breakdown
Allocate realistic times to them
Be prepared to re-plan
Identify milestones – these will often be completion of objectives

## Slide 17: Sequencing activities
Put activities in sequence, with milestones, start dates and durations
e.g.
Set tool evaluation criteria
Draw up list of tools
Evaluate and compare tools
Evaluation Summary
Establish requirements for prototype(s)
Prepare Presentation
Presentation
8/10
15/10
17/10
1/11
5 d
2 d
2 wk
3 wk
1/11
5/11
8/10
1 wk
Critical path – longest path through network – any delay to a critical path activity will delay the final project deliverable.
Notes: Critical path – longest path through network – any delay to a critical path activity will delay the final project deliverable.
Parallel working

## Slide 18: Scheduling
Can use Gantt chart (e.g. MS Project) to show more clearly durations, prerequisites and any overlapping tasks
Use the tool if it helps – pen and paper can be just as effective!

## Slide 19: Re-planning
Necessary if (when)
  Scheduling shows you don’t have enough time
  Once you start, you realise some tasks have been underestimated
      Hofstadter's Law: “It always takes longer than you expect, even when you take into account Hofstadter's Law” [1].
Adjust the plan, keep it up to date
  … but don’t spend more time on the plan than on the project!
        [1] Douglas Hofstadter, Gödel, Escher, Bach: An Eternal Golden Braid, Penguin Books, 1980

## Slide 20: “Rolling Wave” Planning
Some projects may not be clearly enough defined at the start to allow detailed planning
Begin with a skeletal plan, with major deliverables
Add detail as project progresses and decisions are made

## Slide 21: Some final points
Think about relevant development models
  select one to help your planning
  remember you need to plan the whole project
Be realistic in your time estimates
Discuss the plan with your supervisor
Use your plan during the project’s duration
  work towards deadlines, not just the day before hand-in is due
  but be honest if your development model changes
Re-plan when things do not go to plan
Don’t forget to plan for writing all the deliverables!

## Slide 22: Summary
Use project aims and objectives to identify tasks and schedule them
Don’t neglect planning
Don’t put the plan away and forget about it
  a living document
  update it when things go wrong
  use it to help write the dissertation